## Start here
Deployment runbook — women-only fitness app, Egypt
Generated 18 September 2026. Every step is something a person must do; none of it can be written as code.
HOW TO USE THIS
Work top to bottom within each sheet. The 'Blocks' column tells you what cannot start until that row is done.
Set the Status column to In progress / Done as you go. Anything pink is time-critical. Anything amber needs a decision from you, not an action.
THE FOUR THINGS WITH LONG LEAD TIMES — START THESE FIRST
1. PDPL biometric licence (sheet: Egypt — verification & payments). Egypt's data-protection regulations are enforced from around October 2026. You are processing ID cards and selfies, which is biometric data. This is weeks away, not months. It is the single most likely thing to delay launch.
2. ID verification contract with Valify or uqudo. Commercial negotiation plus integration. Without it nobody can sign up, because verification is the product.
3. Payment merchant onboarding (Paymob and/or Fawry). Document verification alone takes about 3 days once you have the papers; gathering the papers takes longer.
4. Content: 124 workout videos filmed with women coaches. This is a production schedule, not a task. Start booking now.
WHAT YOU DO NOT NEED YET
Anything on the Stores sheet beyond creating the accounts. Store listings need finished screenshots, so they come last.
BUDGET AT A GLANCE (recurring costs are the ones that matter)
One-off: Apple Developer 99 USD/year, Google Play 25 USD once, domain ~15 USD/year.
Monthly, driven almost entirely by video: budget for roughly 11 TB/month of video egress at 100k monthly actives. This will dwarf your database bill. Put video behind a CDN and ship download-for-offline at launch.
Firebase: free while testing. You must move to the pay-as-you-go plan before launch, because phone-number sign-in and outbound calls need it.
Amplitude: free tier covers early volume; check the current event limit when you sign up.

## 1. Accounts
ID | Step | Why it matters | Exactly what to do — in plain English | Where to go | What to have ready before you start | Cost | How long it takes | Blocks | Status
A1 | Buy a domain name | Apple and Google both refuse a Gmail address as your developer contact, and you must host your own privacy policy on a URL you control. Nothing else can proceed without this. | Pick a registrar (Namecheap, Cloudflare, or GoDaddy). Buy the domain for the product. Then create two mailboxes on it: one like hello@yourdomain for public contact, one like dev@yourdomain for the developer accounts. Use Google Workspace or Zoho Mail — Zoho has a free tier for one domain. | namecheap.com or dash.cloudflare.com, then zoho.com/mail | The product name, decided. A credit card. | ~15 USD/year + mail (0–6 USD/mo) | 1 hour | A2, A3, L2 | Not started
A2 | Create the Apple Developer account | Required to build, test on a real iPhone, and publish to the App Store. Approval is not instant, so start early. | Go to the Apple Developer site and enrol. Choose Organisation, not Individual — Individual publishes under your personal name, which you do not want for a company. Apple will ask for a D-U-N-S number for an Organisation account; you can request one free from Dun & Bradstreet and it can take up to two weeks, so request it the same day you start. | developer.apple.com/programs/enroll | Legal company name exactly as registered, company address, the dev@ email from A1, a D-U-N-S number, a credit card. | 99 USD/year | 1–14 days (D-U-N-S is the slow part) | S1, S3 | Not started
A3 | Create the Google Play developer account | Required to publish on Android, which is the majority of your market in Egypt. | Go to the Play Console and sign up. Choose Organisation. Google will run identity and business verification and will ask for documents proving the company exists. Pay the 25 USD once — it never renews. | play.google.com/console/signup | Company registration document, company address, the dev@ email from A1, a credit card. | 25 USD one-off | 1–7 days | S2, S4 | Not started
A4 | Create a Google Cloud / Firebase billing account | Firebase's free tier cannot send SMS codes or make outbound network calls. You will hit this wall the first time you test sign-up. | Sign in to the Google Cloud console with the dev@ account, create a billing account, and attach a card. Then set a budget alert at a figure you are comfortable with so a runaway video bill wakes you up by email. | console.cloud.google.com/billing | The dev@ Google account, a credit card. | Pay as you go | 30 min | F1 | Not started
A5 | Create the Amplitude account | This is your analytics. Setting it up after launch means your first month of user behaviour is lost forever. | Sign up with the dev@ email, create an Organisation, then create two projects: one called Production and one called Development. You will get a separate API key for each — never send test data to Production. | amplitude.com/get-started | The dev@ email. | Free to start | 30 min | N1 | Not started
A6 | Create a password manager for the team | You are about to generate a dozen API keys and store credentials. Emailing them to yourself is how they leak. | Set up 1Password or Bitwarden with a shared vault. Every key, every store credential, every service account file goes in there and nowhere else. Never commit a key to the repository. | 1password.com or bitwarden.com | A card (Bitwarden has a free tier). | 0–8 USD/mo | 30 min | Everything | Not started

## 2. Firebase & backend
ID | Step | Why it matters | Exactly what to do — in plain English | Where to go | What to have ready before you start | Cost | How long it takes | Blocks | Status
F1 | Create the Firebase project | This is the backend: sign-in, database, file storage, server functions, crash reporting. | Go to the Firebase console and add a project. Attach the billing account from A4 and switch the project to the Blaze (pay-as-you-go) plan — you cannot send SMS or call an external API on the free plan. Choose europe-west1 or a European region as the default location: it is closer to Egypt than the US and it matters for how fast the app feels. | console.firebase.google.com | The billing account from A4. | Pay as you go | 1 hour | F2–F8 | Not started
F2 | Create a second Firebase project for development | If developers test against the live database, they will eventually delete real users' data. This is not hypothetical. | Repeat F1 with a name ending in -dev. The app points at -dev everywhere except the release build. Never let a developer hold a key to the production project. | console.firebase.google.com | F1 done. | Pay as you go | 30 min | The whole build track | Not started
F3 | Turn on phone-number sign-in | Your product signs people in with a phone number and a four-digit code. No passwords. | In the Firebase console open Authentication, then Sign-in method, and enable Phone. Add your own number under test numbers so developers are not paying for SMS on every test run. Watch the SMS cost per message for Egypt — it is small per message but it is the one cost that scales directly with sign-ups. | Firebase console > Authentication | F1 done. | Per SMS sent | 1 hour | V1, the sign-up flow | Not started
F4 | Create the Firestore database and lock it down | Firestore starts in a mode where anyone on the internet can read everything. This is the most common way a small app leaks all its users' data. | Open Firestore, create the database in Production mode (not Test mode). Then replace the security rules with real ones before any real data goes in. The rule you must get right: a woman can read and write only her own documents, and nobody can read another member's logs, weight, photos or phone number. The architecture plan from the build track gives you these rules as code. | Firebase console > Firestore Database | F1 done, and the security rules from the build track. | Included | 2 hours | All data work | Not started
F5 | Set up Cloud Storage with an image-upload rule | Photos, ID images and video thumbnails live here. An open bucket is a privacy incident. | Enable Storage. Write rules so a woman can upload only into her own folder and read only her own files. Set a maximum file size so nobody uploads a 200 MB file. Critically: your product promises face blur happens on the phone before upload — the bucket must never receive an unblurred image, so this is enforced in the app, not here. | Firebase console > Storage | F1 done. | Per GB stored | 2 hours | Photos, follow-up pictures | Not started
F6 | Set up Crashlytics | Without it you learn your app crashes from a one-star review. | Enable Crashlytics in the console, then have the build track add the SDK to both the Android and iOS builds. Force a test crash from each platform and confirm it appears in the dashboard — do not assume it works. | Firebase console > Crashlytics | F1 done, app builds working. | Free | 1 hour | Launch readiness | Not started
F7 | Set up Remote Config | Lets you turn a feature off without shipping a new app version and waiting for App Store review. You will want this the first time something breaks. | Enable Remote Config and create one flag per risky feature — verification provider, the assistant, payments. Default every flag to off and turn them on deliberately. | Firebase console > Remote Config | F1 done. | Free | 1 hour | Safe launch | Not started
F8 | Decide where video is served from | This is your largest recurring bill by a wide margin. Serving 11 TB a month straight from Storage is the expensive way to do it. | Put a CDN in front of the video: Cloudflare Stream, Bunny.net, or Cloud CDN. Get a price per TB from each and compare against your expected 11 TB a month at 100k actives. Then make download-for-offline a launch feature, not a later one — it cuts egress and it is what women on limited data actually need. | cloudflare.com/products/cloudflare-stream or bunny.net | Your monthly budget ceiling, decided. | Varies — get quotes | 1 day of research | Video delivery | Not started

## 3. Analytics
ID | Step | Why it matters | Exactly what to do — in plain English | Where to go | What to have ready before you start | Cost | How long it takes | Blocks | Status
N1 | Write the tracking plan before any event is sent | If developers invent event names as they go, your analytics become unreadable within a month and cannot be fixed retroactively. | Make a simple spreadsheet listing every event you want, its exact name, and its properties. Keep names consistent — pick one style like session_logged and never deviate. Start with only the events that answer a real question: did she finish sign-up, did she log a session, did her week count, did she come back next week. Twenty good events beat two hundred vague ones. | Your own spreadsheet, then amplitude.com | The MVP feature list. | Free | 1 day | N2 | Not started
N2 | Implement the events and verify them | Events that are implemented but never checked are usually wrong in a way nobody notices for months. | The build track adds the Amplitude SDK and sends the events from the plan. Then you personally walk the app with Amplitude's live debugger open and confirm each event fires once, with the right properties, and never fires twice. Send everything to the Development project while testing. | Amplitude > Data > Live view | N1 done, app running. | Free | 1 day | Launch readiness | Not started
N3 | Do not send anything identifying | Sending a phone number or an ID result into analytics turns a routine analytics tool into regulated personal data. | Use a random internal user ID only. Never send phone number, name, ID verification images or result, weight, photos, or any cycle data to Amplitude. Write this down as a rule in the tracking plan so it survives staff changes. | Amplitude project settings | N1 done. | Free | 1 hour | PDPL compliance | Not started
N4 | Budget for Amplitude, or choose a cheaper analytics plan | At the 100,000 monthly users you are planning for, Amplitude is well past its free tier. This is a recurring bill nobody had costed, and it is roughly 15 to 30 times your entire server bill. | Amplitude is free to 50,000 monthly tracked users. At 100,000 expect roughly $1,000-$2,500 a month depending on the plan. Decide before launch: (a) budget for it, (b) negotiate a startup rate with their sales team, or (c) use a cheaper product. Get the quote in writing before you wire the app to it, because moving analytics later means losing your history. | amplitude.com/pricing, then their sales team | Your expected user numbers for year one. | $1,000-$2,500/month at 100k users | 1 week to get a quote | Your running costs | DECIDE NOW

## 4. Verification & payments
ID | Step | Why it matters | Exactly what to do — in plain English | Where to go | What to have ready before you start | Cost | How long it takes | Blocks | Status
V1 | Get the PDPL biometric processing licence | Egypt's Personal Data Protection Law executive regulations (Decree 816 of 2025) require explicit consent plus a licence to process biometric data. You scan ID cards and match selfies — that is biometric. Enforcement lands around October 2026, which is now. | Engage an Egyptian data-protection lawyer this week. Ask them exactly three things: what licence or registration you need with the Personal Data Protection Centre, what the application requires, and how long it takes. Then apply. Do not let a developer decide this — it is a legal filing. | Via an Egyptian lawyer; the Personal Data Protection Centre | Company registration, a written description of what data you collect and why, your retention policy (ID images deleted after the check, result kept). | Legal fees + filing | Weeks — start now | Launch, legally | Not started
V2 | Sign the ID verification contract | Nobody can join the app without this. Verification is not a feature here, it is the gate that makes a women-only community real. | Contact both Valify (Egyptian, licensed, checks against the National Registry) and uqudo (covers the Egyptian ID with liveness and face match). Ask each for: price per check, sandbox access, expected pass rate on Egyptian IDs, and whether they return the sex digit from the ID number. Get a sandbox key and have the build track integrate against it before you sign anything. | valify.me and uqudo.com | V1 in progress, company registration, expected monthly volume. | Per verification — negotiate | 2–6 weeks | Sign-up flow entirely | Not started
V3 | Sign the data-processing agreement with the verification provider | They will be handling ID cards and faces on your behalf. Without a written agreement you carry all the legal risk. | Have the lawyer from V1 review and sign a data-processing agreement with whichever provider you choose. It must state that ID images and selfies are deleted after the check and that only the result is retained — because that is what your app promises on screen, and a promise you cannot evidence is a liability. | Via your lawyer + the provider | V2 provider chosen. | Legal fees | 1–2 weeks | Launch, legally | Not started
V4 | Arrange the woman-reviewer path | Your app promises that a woman reviews any check the system cannot decide, and that women who wear niqab have an alternative. Someone has to actually be there. | Decide who does this and what it pays. Write the review procedure down. If you are using partner ladies-only gyms for in-person checks, sign agreements with them — the app currently claims 12 partner gyms in Cairo, Giza and Alexandria, and that claim must be true before launch. | Internal + partner gyms | V2 done. | Staff cost | 2–4 weeks | Sign-up edge cases | Not started
P1 | Open a payment gateway merchant account | Needed only when you turn on paid coaching. Not required for the recommended MVP cut — but onboarding is slow, so start it in parallel. | Register with Paymob and with Fawry. Paymob verifies documents in about three days once you submit them. You will typically need the Commercial Register, tax card, owner's ID and a company bank account. Anything not already in Arabic must be translated by a certified translator or it will be rejected. Ask both for their fee per transaction and settlement time, then choose. | egypt.paymob.com/portal2/en/register and fawry.com | Commercial Register, tax card, owner ID, company bank account, certified Arabic translations. | Per transaction — negotiate | 2–4 weeks | Coaching payments | Not started
P2 | Decide how coaches get paid out | Your product promises coaches keep 80% and are paid on the 1st of the month to a mobile wallet or bank account. That payout has to actually run. | Work out whether you pay coaches manually at first (entirely reasonable at low volume) or automate it. Confirm with your bank and with Paymob what is possible for paying out to Vodafone Cash and similar wallets. Whatever you choose, the 80% figure is on screen, so the maths must be exact. | Your bank + Paymob | P1 in progress. | Transfer fees | 1–2 weeks | Coach payouts | Not started

## 5. App stores
ID | Step | Why it matters | Exactly what to do — in plain English | Where to go | What to have ready before you start | Cost | How long it takes | Blocks | Status
S1 | Create the app record in App Store Connect | Reserves your app name and gives the build somewhere to upload to. | In App Store Connect create a new app. Reserve the product name — do this early, names get taken. Set the primary language and the bundle identifier, which must match what the build uses and cannot be changed later. | appstoreconnect.apple.com | A2 done, product name decided. | Included in the 99 USD | 1 hour | S3 | Not started
S2 | Create the app record in Play Console | Same purpose on the Android side. | In Play Console create the app, set the default language to Arabic or English (you support both), and set the package name, which is also permanent. | play.google.com/console | A3 done. | Included in the 25 USD | 1 hour | S4 | Not started
S3 | Fill in Apple's App Privacy questionnaire | Apple asks exactly what data you collect and will reject you for answering wrongly. Your app collects unusually sensitive categories, so this needs care. | Answer honestly for every category you touch: phone number, health and fitness, photos, and any cycle data. Declare that ID images are deleted after verification. Wrong answers here are a rejection and a delay, and a dishonest answer is worse than a delay. | App Store Connect > App Privacy | F1 done so you know what is actually collected. | Free | Half a day | iOS release | Not started
S4 | Fill in Google's Data safety form | The Android equivalent, with the same consequences. | Same content as S3. Google additionally asks whether data is encrypted in transit and whether users can request deletion. Your app offers account deletion in settings, so say yes — and make sure that button genuinely deletes. | Play Console > App content > Data safety | F1 done. | Free | Half a day | Android release | Not started
S5 | Prepare store listings and screenshots | This is the shopfront. It is also where your product guardrails apply hardest. | Write the listing in Arabic and English. Take screenshots at the exact sizes each store demands. Follow your own brief's rules: no before-and-after body photos, no weight-loss promises, no timelines, no calorie-deficit talk, and no member faces without written consent. Those rules exist for the product and apply to the shopfront too. | App Store Connect and Play Console | A finished app to screenshot. | Design time | 2–3 days | Both releases | Not started
S6 | Set up internal testing tracks | You want your own team on the real app before strangers are. | On Android use an Internal testing track in Play Console. On iOS use TestFlight. Add the team's emails. Expect the first iOS review for TestFlight to take a day or two. | TestFlight and Play Console > Testing | S1, S2 done, a build that compiles. | Free | 1 day | Real testing | Not started
S7 | Submit for review and expect to be rejected once | First submissions usually come back. Plan for it rather than being surprised. | Submit to both. Apple review is typically a day or two but can be longer for an app that handles ID documents — give the reviewer a test account and clear notes explaining the verification flow, or they will not be able to get past sign-up and will reject you for it. Have a named person watching for the reviewer's questions. | App Store Connect and Play Console | Everything above done. | Free | 1–2 weeks with one rejection | Launch | Not started

## 6. Content & people
ID | Step | Why it matters | Exactly what to do — in plain English | Where to go | What to have ready before you start | Cost | How long it takes | Blocks | Status
C1 | Film the workout videos | The app promises 124 videos filmed by women coaches, with form cues and a quieter alternative for each. Without them there is no product. | Book women coaches and a shoot. Work from the exercise list the build track extracts from the prototype. For each move you need the demo clip, three form cues, and a named easier or quieter alternative. Film vertical. Keep files small — your users are on limited data, and this is also your biggest hosting cost. | Internal production | The exercise list, coaches booked, a location. | Production budget | 4–8 weeks | Train tab entirely | Not started
C2 | Build the food and recipe library | One-tap meal logging only works if Egyptian dishes are in the database with real portions. | Assemble the food list with verified values — dishes measured in bowls, loaves and spoons, not grams. Where you cannot verify a dish's nutrition, the product's rule is to show no totals rather than invented ones, so mark those explicitly. Add cost per serving in EGP for recipes. | Internal + a nutrition data source | A verified nutrition data source. | Data licence + time | 3–6 weeks | Eat tab entirely | Not started
C3 | Staff moderation | Your Safety Centre promises a woman moderator reads a report within an hour. That is a staffing commitment, on screen, in writing. | Decide the hours you can genuinely cover and who covers them. If you cannot honestly promise one hour, change the number on the screen before launch rather than breaking the promise. Write the moderation procedure: what is removed, what is a warning, what is a ban. | Internal | The community rules from the pledge screen. | Staff cost | 2–4 weeks | Community launch | Not started
C4 | Recruit the first coaches | An empty coaching marketplace looks abandoned. Not needed for the recommended MVP cut, but it takes time. | Find qualified women coaches, check their certificates yourself, and help them build their page. Aim for enough that a client browsing sees a real choice. | Internal outreach | Coach onboarding flow built. | Time | 4+ weeks | Coaching launch | Not started
C5 | Add allergen and diet tags to the food library | The allergy safety check cannot work at all without this. Knowing a dish is 'koshari' does not tell the app whether it contains nuts. | For every dish in the food library, fill in two extra columns: which of the common allergens it contains (nuts, dairy, egg, gluten, shellfish, sesame), and which diets it suits (vegetarian, vegan). Anything you are unsure about must be left blank and treated as unsafe, never guessed. | Your food/content spreadsheet, before it is loaded into the app | The food library itself, and someone who knows Egyptian cooking. | Content time | 1-2 weeks | The allergy check; the Eat screens | Not started
C6 | Write the starting programmes | When a woman finishes setup, the app offers her a starting programme. There is currently no programme content written at all, so that screen has nothing to show and setup cannot finish. | Have your coach write the starting programmes — at minimum one per goal, for each of home-with-nothing, home-with-dumbbells, and gym. Each needs its days, its moves in order, and its sets and reps. The moves must come from the 124-move library so the videos exist. | Your head coach, into the content spreadsheet | The 124-move library agreed and filmed. | Coach time | 2-3 weeks | The last setup screen; every woman's first session | Not started
C7 | Hire and roster the women reviewers | Roughly 640 checks a month need a human at 8,000 sign-ups, and the busiest hours are 7-11pm Cairo. The promise on the waiting screen is only as good as the roster behind it. | Hire at least two women reviewers covering the evening shift, and agree the target response time before it is written on the screen. They review ID checks the automatic system could not decide, and the niqab video path. | Your hiring process | The decision on the Safety Centre promise above. | 2 part-time salaries | 3-4 weeks | The waiting-for-a-reviewer screen; the niqab path | Not started
C8 | Tag every exercise with what it must not be used for | SAFETY, and it blocks two features. When a woman is told to avoid deep knee bends, or a screening says refer her to a physio, the app has to remove those moves from what a coach can pick. It cannot do that today because no move carries that information. Two separate planners found this independently. | For each of the 124 moves, add one column listing what it loads or risks - for example: deep_knee_flexion, high_impact, jumping, pelvic_floor_load, overhead, prone, supine_after_first_trimester. Your coach and a physiotherapist should agree the list of tags first, then tag every move. Anything left untagged is treated as unsafe and hidden, never shown as safe. | Your exercise content spreadsheet, before it is loaded into the app | The 124 moves agreed, and a physiotherapist to review the tag list. | Coach + physio time | 1-2 weeks | The avoid list; postnatal and injury screening; the coach's move picker | Not started

## 7. Legal & your decisions
ID | Step | Why it matters | Exactly what to do — in plain English | Where to go | What to have ready before you start | Cost | How long it takes | Blocks | Status
L1 | Decide the minimum age | The app reads date of birth from the national ID, so it can enforce whatever you choose — but you must choose, and a lawyer must confirm it. | Decide 16 or 18 and get it confirmed in writing by your Egyptian lawyer. It affects consent validity and your store declarations. | Via your lawyer | A lawyer engaged. | Legal fees | 1 week | Sign-up rules | Not started
L2 | Write and host the privacy policy and terms | Both stores require a policy at a URL you control, and PDPL requires you to say what you do with data. | Have the lawyer draft both. The privacy policy must match what the app actually says on screen — that ID images are deleted after the check, that only the result is kept, that cycle data is private by default and deletable on its own. Host it on the domain from A1. | Your lawyer, then your own site | A1 done, a lawyer engaged. | Legal fees | 2 weeks | S3, S4, both releases | Not started
L3 | Write the membership policy | Your product is women-only. Who counts as a member is a policy question with legal consequences, and an Australian court has already ruled that excluding someone on gender-related appearance is discrimination. | Have your lawyer draft the written policy, including how it treats trans women. Your app deliberately never classifies a face — the gate is the ID document. Keep it that way, and make the written policy match the built behaviour. | Via your lawyer | A lawyer engaged. | Legal fees | 2 weeks | Launch, legally | Not started
L4 | Decide the product name and get the Arabic wordmark | Still marked as open in the product brief. Everything downstream — domain, store records, bundle identifiers — depends on it and much of it is permanent. | Choose the name, check it is free on both stores and as a domain, and have the Arabic wordmark designed. Then do A1. | Internal + a designer | Nothing — do this first. | Design fee | 1 week | A1, S1, S2 | Not started
L5 | Decide the two product questions still open from the design | Both are on screen already and both are yours, not the build team's. | One: follower counts are currently visible in the community, which reverses an earlier decision made to avoid turning the app into a comparison engine. Two: client before-and-after results now exist behind in-app consent the client can withdraw, which softens the brief's absolute ban on before-and-after photos to apply to your own marketing only. Confirm or reverse each. | Internal | Read the community and coach-results screens in the prototype. | Free | 1 hour | Final design sign-off | Not started
L6 | Decide the length of the verification code — DONE | The code screen is the second thing a woman ever sees. Firebase sends a six-digit code and that cannot be changed; every screen and every Arabic string in the app currently says four. One of the two has to move. | Settled: six digits, because that is what Firebase sends and it cannot be configured. Already implemented — the code screen now shows six boxes, and the wording in both English and Arabic was changed to match. Nothing further is needed from you unless you want to reverse it, which would mean contracting an Egyptian SMS provider directly. | A decision from you; then the change is made in the app | Nothing. This is a five-minute decision. | Free (option a) | 5 minutes | The whole sign-up flow | Done
L7 | Decide where allergies and dietary needs get collected | SAFETY. The Eat screens check every meal against her allergies — but in the launch scope there is no screen that ever asks for them. Two separate planners found this independently. Until it is fixed the app must treat allergies as 'unknown' and interrupt women who have none. | Choose the screen that asks. Simplest is to add one step to the setup questions she already answers when she joins (the 'Where and with what' / 'Life stage' sequence). Alternative is a row in Profile and settings, but then most women never set it and the safety check stays blind. | A decision from you; then one screen is designed and built | Nothing. | Free | 1 hour to decide | The food safety check; the Eat screens | DECIDE NOW
L8 | Decide what the first week looks like at launch | The five-step first week ends with 'join a group' and 'add a follow-up picture'. Both live in Community, which is not in the launch scope — so no woman can ever finish it, and the completion screen is unreachable. | Pick one. (a) Cut it to the three steps that do work at launch — log a set, log a meal, finish a session. (b) Pull one Community screen into the launch scope, which is more work and more moderation. We recommend (a); it needs only a copy and count change. | A decision from you | Nothing. | Free | 15 minutes | The first-week screens | DECIDE NOW
L9 | Fix what the Safety Centre promises | The Safety Centre screen currently promises BOTH 'a moderator will look within an hour' AND 'a human is here 9am to 9pm'. Those contradict each other, and a promise on screen is a promise you must staff. No code can keep it. | Decide the real promise based on the people you will actually hire, then the screen is reworded to match it exactly. If it is 9am-9pm, say that and nothing more. Never leave a response time on screen that the roster cannot meet. | A decision from you, with whoever runs moderation | Your moderation staffing plan. | Staff cost | 1 hour | The Safety Centre screen; your legal exposure | DECIDE NOW
L10 | Rule on what a repaired week is worth | When a woman misses her weekly goal, a banked rest week repairs it automatically so her total is protected. Nobody has decided whether that repaired week also PAYS her points, and whether it counts toward earning the next rest week. Without a ruling the reward maths is guesswork. | Decide two things. One: does a week that was repaired by a rest week award points? (The recommendation is no - the protection is the reward.) Two: does it earn progress toward the next rest week? (The recommendation is also no, or rest weeks become self-renewing and the goal stops meaning anything.) Say yes or no to each. | A decision from you | Nothing. | Free | 15 minutes | The rewards maths; the progress screens | DECIDE NOW
L11 | Confirm the five tier thresholds - two screens currently disagree | The tiers a woman climbs were never written down, so they were inferred from the screens - and the copy on 'When a tier slips' contradicts the copy on 'Your progress'. Whichever is built, one of the two screens will be wrong. | Write down the five tiers and exactly how many counted weeks each one needs, then the two screens are made to match it. This is your product's reward ladder; it should be a decision, not something reverse-engineered from a mockup. | A decision from you, with whoever owns the product | Nothing. | Free | 1 hour | The progress and tier screens | DECIDE NOW
L12 | Settle with Apple whether coaching is a service or digital content | POSSIBLE LAUNCH BLOCKER, and no code can fix it. If Apple decides that paying a coach through your app is 'digital content', it must go through Apple's own payment system and Apple takes 30%. Your plan gives the coach 80%. 80 + 30 is more than 100, so on iPhone the business model would not work at all. | Do this BEFORE you build the payment screens. Write to Apple via App Review Support and describe the service exactly: a woman pays a named human coach for personal training delivered over weeks, and the app takes a commission. Ask them to confirm in writing whether this falls under 'physical services outside the app' (your own payment rails, no Apple cut) or 'digital content' (Apple's payment system, 30%). Keep their written answer. If they say digital content, your options are: raise prices on iPhone, lower the coach's share on iPhone only, or move payment out of the app entirely to a website. | App Store Connect > App Review > Contact Us, in writing | A clear written description of what a woman actually buys, and your commission rate. | Free to ask; potentially 30% of all iPhone revenue | 2-4 weeks for a written answer | Every payment screen; the coach's 80% share; the iPhone release | DECIDE NOW
L13 | Choose the payment rail, because it changes what the app can promise | Two screens currently promise different things. One says 'she pays only once you accept'. The other takes payment first. Holding a payment without taking it is possible on cards, but NOT on Fawry or mobile wallets - so on those rails, 'pay only when accepted' cannot be built at all. | Decide with Paymob which rails you launch with. If you want 'pay only when the coach accepts', you need card payments that support an authorisation hold, and the two screens must say so. If you launch with Fawry and wallets, the money is taken up front and the wording on both screens must change to match, with a refund if the coach declines. Get the answer in writing from Paymob before the screens are built. | Paymob, during merchant onboarding | Commercial registration, and the decision above about Apple. | Processing fees | 2-3 weeks | The enquiry and checkout screens; refunds | DECIDE NOW

## 8. Build track (for reference)
ID | Step | Why it matters | Exactly what to do — in plain English | Where to go | What to have ready before you start | Cost | How long it takes | Blocks | Status
B1 | Decide the MVP scope cut | 131 features is not an MVP. Everything else in the build depends on this one decision. | Read section 0 of BUILD-BRIEF.md and either accept the recommended cut (client-only, ~55 screens, verification kept) or give a different one. Do not average two answers. | BUILD-BRIEF.md in the project root | Nothing. | Free | 1 hour | The entire build | Not started
B2 | Install the Flutter toolchain — DONE | No code can be compiled or tested until this exists. Flutter, Dart, the Android SDK and Xcode are all currently missing or incomplete on the build machine. | Done on this machine. Flutter 3.47.4 and Dart 3.13.3 are installed, the Android toolchain builds, and the test suite runs. Two things were missing and had to be added: the Android SDK 'command-line tools' component, and a Java runtime (macOS ships a fake 'java' that reports no runtime installed). | docs.flutter.dev/get-started/install | A Mac with ~15 GB free. | Free | Half a day | All code | Done
B3 | Write the test cases | Written before code, on purpose, so that the product's research-backed rules cannot be quietly broken during implementation. | Follow section 5 of BUILD-BRIEF.md. Priority P0 is the journeys that are the product; P1 is one test per non-negotiable rule, written so it fails if the rule is violated. | BUILD-BRIEF.md section 5 | B1 done. | Agent time | 1 session | B5 | Not started
B4 | Plan each feature group | Eight groups, one plan each, with a data model, the query and index for every screen, offline behaviour, and security rules as code. | Follow section 6 of BUILD-BRIEF.md. A plan without its rejection-contract items is not finished. | BUILD-BRIEF.md section 6 | B1, B3 done. | Agent time | 1 session | B5 | Not started
B5 | Implement | Flutter UI plus domain, data layer, backend, platform channels and both stores' build configuration. Not the frontend alone. | Follow section 7 of BUILD-BRIEF.md. Generate from tokens.mjs and the ARB files rather than retyping design values or strings. | BUILD-BRIEF.md section 7 | B2, B4 done. | Agent time | Multiple sessions | B6 | Not started
B6 | QA against three sources | Comparing only against the design misses violated domain rules, which is where this product is most fragile. | Follow section 8 of BUILD-BRIEF.md: compare against the prototype, the feature list, and the test cases, on both platforms, in both languages. | BUILD-BRIEF.md section 8 | B5 done. | Agent time | 1 session | Launch | Not started
B7 | Install Xcode so the app can be built for iPhone | This is the one build step that cannot be done for you. Without it the app can never be put on an iPhone or submitted to Apple, and every iPhone row in the test plan stays untested rather than passing. | On the Mac, open the App Store, sign in with your Apple ID and install Xcode (large, about 40 GB, takes a few hours). Then open a terminal and run, one line at a time: sudo xcode-select --switch /Applications/Xcode.app/Contents/Developer then sudo xcodebuild -runFirstLaunch then sudo gem install cocoapods. Confirm it worked by running: flutter doctor — the Xcode line must show a tick. | App Store on the Mac, then the Terminal app | Your Apple ID, the Mac's password, and about 40 GB free. | Free | Half a day, mostly downloading | Every iPhone build and the App Store submission | URGENT - only you can do this
B8 | Replace the placeholder app identifier | The app is currently identified as 'com.example.fitness_app'. Both Apple and Google reject anything starting with com.example, so it must change before the first upload — and changing it later resets your store listing. | Once you have chosen the product name, tell us and it is changed in one place. It is usually your website address backwards — for example if your site is sabaya.eg the identifier would be eg.sabaya.app. Choose it once; it can never be changed after the first release. | A decision from you; then we change it in the project | The product name decided (see the product questions in sheet 7). | Free | 15 minutes | Both store submissions | DECIDE NOW