## Start here
Own Hub, your launch runbook
Updated 24 September 2026. This replaces the 22 September version.
What changed, and why this got much shorter
The first release is Today, Train, Eat, My cycle and Progress, with no account. Accounts, the community, the coach side, payments and the assistant are switched off until there is a back end to support them honestly.
So you do not need Firebase to ship. The old sheet spent its first sixteen steps standing up a backend. All of that moved to the "Later, release 2" tab. Nothing is lost, it is simply not in your way now.
How we work through it
1. Open the "Your steps" tab. The steps are in order. Do them top to bottom.
2. Yellow rows are yours. Green rows are mine. Orange rows are a decision only you can make.
3. When you start one, tell me the number: "I am starting step 4". I will give you the exact commands, the exact values, and check the result with you.
4. Mark the Status column as you go. Nothing else in the sheet needs editing.
The three things that decide your timeline
Apple approval takes one to two days. Google identity verification takes one to three days. Google then requires a 14 day closed test with 12 real testers before you may go to production. Start those three early and everything else fits around them.
What is already done
The app builds on both platforms, 3,671 tests pass, the store listings and privacy answers are written, the ten screenshots are taken, the 40 second video is cut, and the pre-flight script refuses a bad submission. Four things are left that only you can provide, and they are steps 1, 2, 5 and 7.

## Do now, free
What you can do today, for nothing
Everything that costs money is parked: the two developer accounts, the domain and the lawyer. These four cost nothing, they are yours rather than mine, and the first two clear half of what currently blocks a submission.
# | Step | Exactly what to do | Done when | Status
A | Create the Android signing key | You already have a JDK (Homebrew OpenJDK 17), so nothing needs installing. Run this yourself, because it asks for a password twice and that must not go through a chat: mkdir -p ~/keys && /opt/homebrew/opt/openjdk@17/libexec/openjdk.jdk/Contents/Home/bin/keytool -genkey -v -keystore ~/keys/ownhub-upload.jks -keyalg RSA -keysize 2048 -validity 10000 -alias upload Then back the file and the password up in a password manager AND one offline place. If both are lost and Play App Signing is off, the app can never be updated again. Never put the .jks inside the project. | The file exists at ~/keys/ownhub-upload.jks | Not started
B | Write android/key.properties | Four lines: storePassword, keyPassword, keyAlias=upload, and storeFile as the absolute path to the .jks. Type it yourself so the passwords stay off the chat. The file is already gitignored. Tell me when it is there and I will verify the release build is signed with your key rather than the debug fallback, which is what Play refuses. | The preflight stops saying the bundle is signed with the DEBUG key | Not started
C | Publish the four pages, free | The sheet assumes a bought domain, but Cloudflare Pages has a free tier with no card. Publish /privacy, /terms, /support and /delete-account there and use that subdomain for now. The full text of all four is already written in docs/release (privacy-policy.md, terms.md, delete-account.md). Moving to your own domain later is a one line change. Worth doing early: a missing or broken support page is one of the three most common first submission rejections. | All four open on a phone browser, not just on your Mac | Not started
D | Say yes or no to the app icon | There is an icon: a typographic monogram in the brand rose, drawn from the product's own design language, because the project has never had a logo file. If you have a mark, hand me the 1024 by 1024 PNG with no transparency and I regenerate every size in a minute. If not, the one there ships. This costs nothing and blocks nothing, but it is the first thing anyone sees. | You have said keep or replace | Not started
Parked until you want to spend
Apple Developer 99 USD a year, Google Play 25 USD once, the domain, and the lawyer. All four have other people's waiting time attached: Apple approves in 1 to 2 days, Google verifies identity in 1 to 3, and Google then requires a 14 day closed test with 12 real testers before production. So whenever you do start them, start them first and let the rest run alongside. Everything in "Your steps" that depends on them is greyed out there.

## Your steps
Own Hub, every step to the two stores, in order
Yellow = you do it. Green = I do it. Orange = a decision only you can make. Tell me the step number when you start one.
# | Step | Who | Where | Exactly what to do | You'll need | Done when | Time | Watch out | Status
PHASE 1, the two accounts. Start these first, they have waiting time. (about 1 hour of your time)
1 | Enrol in the Apple Developer Program | You | developer.apple.com/programs/enroll | Enrol as Individual, or as Organization if Own Hub is a registered company. Pay the 99 USD a year. Approval usually lands in 24 to 48 hours. When it does, sign in to appstoreconnect.apple.com and accept the Paid Apps Agreement under Agreements, Tax and Banking, even though the app is free: an unaccepted agreement blocks submission. | Apple ID with two factor on, a government ID, a card | You can sign in to App Store Connect and the agreement shows Active | 30 min | Organization enrolment needs a D-U-N-S number, which can take up to 30 days. Individual is instant by comparison. | On hold, 99 USD a year
2 | Open a Google Play developer account | You | play.google.com/console | Register with the Google account that will own this app forever, not a personal Gmail you might lose. Pay the 25 USD once. Complete identity verification with a photo of a government ID: the name must match your Google Payments profile exactly. | A dedicated Google account, a government ID, a card | The console stops showing the verification banner | 30 min | A personal account created after 13 Nov 2023 must run a 14 day closed test with 12 testers before production. That clock is step 13, start it as early as you can. | On hold, 25 USD once
PHASE 2, the four values the app needs from you (about 1 hour, plus the domain)
3 | Give me your Apple Team ID | You then me | developer.apple.com/account, Membership | Copy the ten character Team ID. Paste it to me in this chat, or put it in ios/ExportOptions.plist where it currently says YOUR_TEAM_ID. It is not a secret. | Your approved Apple account (step 1) | The pre-flight line "team id filled in" says PASS | 5 min | This is the Team ID, not the App ID and not your Apple ID email. | Waits on step 1
4 | Create the Android signing key, and back it up | You | Terminal on your Mac | You already have a JDK: Homebrew OpenJDK 17, which is why this command names it in full rather than asking you to install anything. Run it yourself, because it asks for a password twice and that password must never be pasted into a chat: mkdir -p ~/keys && /opt/homebrew/opt/openjdk@17/libexec/openjdk.jdk/Contents/Home/bin/keytool -genkey -v -keystore ~/keys/ownhub-upload.jks -keyalg RSA -keysize 2048 -validity 10000 -alias upload It asks for: a keystore password twice, then your name, unit, organisation, city, state, and the two letter country code EG, then "is this correct" (type yes), then a key password where Return reuses the first one. | A password you have never used elsewhere | The file exists at ~/keys/ownhub-upload.jks | 10 min | Never put this file in the project folder or in git. If you lose it and Play App Signing is off, you can never update the app again. | DO NOW, free
5 | Tell the app where the key is | You then me | app/android/key.properties | Create that file with four lines: storePassword, keyPassword, keyAlias=upload and storeFile pointing at the absolute path of the .jks. The file is already gitignored, so it never leaves your machine. Do not paste the passwords into this chat: type them into the file yourself. | The passwords from step 4 | A release build is signed with UPLOAD rather than the debug key, which the pre-flight reads off the bundle itself | 5 min | Use the full path, starting with /Users/. A relative path silently falls back to debug signing. | Waits on step 4
6 | Buy a domain and publish four pages | You | Any registrar, then Cloudflare Pages or GitHub Pages | Buy the domain. Publish four pages that load with no login and no cookie wall: /privacy, /terms, /support and /delete-account. The full text for all four is already written in docs/release: privacy-policy.md, terms.md and delete-account.md. Support can be a page with a monitored email address. | A domain, a static host, the three documents | All four URLs open on a phone browser, not just on your Mac | 2 hours | A parked domain or a 404 on the support page is one of the three most common first submission rejections. | On hold, or free on Cloudflare Pages, see the free tab
7 | Put the four addresses into the app | You then me | app/lib/config/legal_links.dart | Four constants, currently empty strings. Fill them with the four URLs from step 6. Until they are filled the app does not draw its privacy and terms rows, and the pre-flight refuses to submit. | The live URLs from step 6 | The pre-flight line "legal links filled in" says PASS, and Profile, Privacy shows the two rows | 5 min | They must be the live https addresses, not a draft preview link. | Waits on step 6
PHASE 3, decisions and artwork (about 1 hour, plus the lawyer)
8 | Decide whether to keep the app icon | Decision | app/assets/icon/icon-1024.png | There is an icon: a typographic monogram in the brand rose, drawn from the product's own design language, because the project has no logo file. If you have a mark, give me the 1024 by 1024 PNG with no transparency and I will regenerate every size. If not, the one there ships. | Your mark, if you have one | You have said keep or replace | 5 min | No alpha channel and no rounded corners. Apple rejects an icon with transparency; both systems apply their own mask. | DO NOW, free
9 | Have the policy, terms and deletion page reviewed | You | An Egyptian lawyer | Send the three documents from docs/release. Ask specifically about Egypt's PDPL, about a women only membership rule, and about the minimum age. | The three documents | The lawyer has signed off, or has given you edits | 1 week | This runs in parallel with everything else. Start it early. | On hold, lawyer
10 | Decide the minimum age, 16 or 18 | Decision | With your lawyer | It must match the terms, the policy and the age rating on both stores. It does not block this release, which has no accounts, but the store forms ask. | Legal advice | A number you can put in three places | 15 min | Do not include under 13 anywhere: that puts you in the Families policy, which is far stricter. | Waits on step 9
PHASE 4, the two store listings (about 3 hours, everything is pre-written)
11 | Create the app in App Store Connect | You | appstoreconnect.apple.com | My Apps, then plus, then New App. Platform iOS, bundle ID com.ownhub.app, SKU ownhub-ios-001. Then fill every field from docs/release/appstore-listing.md, which has the name, subtitle, description, keywords and the exact App Privacy answers, in English and Arabic, with the character counts already measured. | appstore-listing.md, the ten screenshots | The version page has no red warnings left | 90 min | Answer App Privacy as Data Not Collected. That is true of this release and the document explains why, which is what you say if they ask. | Waits on step 1
12 | Create the app in Play Console | You | play.google.com/console | Create app, then work down the Set up your app checklist. Every answer is in docs/release/play-listing.md, including the Data safety form question by question and the IARC content rating answers. Upload the feature graphic from docs/release/screenshots/play-phone/. | play-listing.md, the screenshots, the feature graphic | Every item in the dashboard checklist is green | 90 min | Data safety is the form that most often causes a rejection. Copy the answers from the document rather than improvising them. | Waits on step 2
PHASE 5, test on real phones, then submit (2 weeks, mostly waiting)
13 | Build and upload the two artifacts | Me | This chat | Once steps 3 to 7 are done I build the signed app bundle for Play and the signed archive for Apple, run the pre-flight until every line passes, and hand you the two files with the exact upload steps. | Steps 3 to 7 finished | app-release.aab and the .ipa exist and are signed with your keys | 30 min | Nothing for you to do here. | Waits on 3 to 7
14 | Start Google's 14 day closed test | You | Play Console, Testing, Closed testing | Create a track, upload the bundle, and add 15 to 20 real Google accounts as testers, so you still have 12 after dropouts. Send them the opt in link. They must actually install and open the app, and keep it installed for the full fourteen days. | The bundle, 15 to 20 women willing to test | The Testers tab shows 12 or more opted in, continuously, for 14 days | 14 days | Google checks real engagement. Bought or fake testers risk permanent account termination. | Waits on step 2
15 | Test it yourself on a real iPhone and a real Android | You | TestFlight, and the bundle installed on an Android | Install from the exact artifact being submitted. Walk the eight journeys in docs/qa/02-QA-REPORT.md. Then do the two that matter most here: log a session, force quit the app, reopen it and check your week is still there. Then delete everything from Profile and check it does not come back. | Your iPhone, one Android phone | Both walks pass on both phones | 2 hours | Test the release build, not a debug build from your Mac. They behave differently. | Waits on step 13
16 | Apply for Play production access | You | Play Console dashboard | After the 14 days, answer their questions about how you recruited testers, what feedback you got and what you changed. Write real specifics: generic answers get denied. | Notes from your testers | Google grants production access, usually within 7 days | 30 min | Only for personal accounts. An organization account skips this entirely. | Waits on step 14
17 | Submit to both stores | You | App Store Connect, and Play Console | Apple: Add for Review, and choose Manually release so approval does not publish before Android is ready. Google: create a production release and roll out. Apple typically reviews within 24 to 48 hours; Google's first review can take up to 7 days. | Everything above | Both say In Review, then Approved | 1 hour | Keep the phone number in App Review Information one you will answer for a week. Apple does call. | Waits on everything

## Values and files
Everything the project needs from you, and exactly where it goes
There are no API keys and no environment variables in this release. It makes no network calls at all, so there is nothing to configure and nothing that can leak.
What | Exactly what it looks like | Where it goes | Secret?
Apple Team ID | Ten characters, like A1B2C3D4E5 | ios/ExportOptions.plist, replacing YOUR_TEAM_ID | No, it is public
Upload keystore | ownhub-upload.jks, one binary file | ~/keys/ , never inside the project | YES. Losing it ends your ability to update
Keystore passwords | Two passwords you choose | app/android/key.properties, and your password manager | YES. Do not paste them into this chat
Key alias | upload | app/android/key.properties | No
Privacy policy URL | https://yourdomain/privacy | app/lib/config/legal_links.dart, privacyPolicy | No
Terms URL | https://yourdomain/terms | app/lib/config/legal_links.dart, terms | No
Support URL | https://yourdomain/support | app/lib/config/legal_links.dart, support | No
Deletion URL | https://yourdomain/delete-account | legal_links.dart, deleteAccount, and Play Data safety | No
App icon master | icon-1024.png, 1024 by 1024, no transparency | app/assets/icon/ , then I regenerate every size | No. One already ships if you keep it
App name on the stores | Own Hub, 26 of 30 characters | Both consoles, already written in the listing documents | No
Bundle ID and applicationId | com.ownhub.app | Already set in both projects. Permanent after first publish | No
Version | 1.0.0+1 in app/pubspec.yaml | Bump the number after the plus on every single upload, to either store | No. Never reuse a build number
Reviewer credentials | Not needed | This release has no account, so both consoles say no sign in required | n/a

## Decisions
Choices only you can make
Decision | Why it matters | My recommendation
Keep the generated app icon, or supply your mark | It is the first thing anyone sees, and it is the one piece of the brand the project has never had as a file. | Ship the monogram now. It is on brand and it is honest. Replace it whenever your mark exists: it is a one minute regeneration.
Apple account: Individual or Organization | It decides the seller name shown on the App Store, and it cannot be changed later. | Organization if Own Hub is a registered company, because a company name reads as more serious to a woman handing over her training. Individual if not: it is instant.
Play account: personal or organization | A personal account must run the 14 day, 12 tester closed test. An organization account does not. | If you have the company papers, organization saves you two weeks. If not, start the closed test on day one and let it run while you do everything else.
Minimum age, 16 or 18 | It must match the terms, the policy and both age ratings. | Ask the lawyer. 18 for anything you will later charge for.
Whether the video is used as a store preview | The 40 second video shows the community and the coach side, which this release does not ship. A store preview showing features the binary lacks is a rejection. | Use it for social, for investors and on the website. If you want a store preview, say so and I will cut a version that shows only what ships.
When the community and coaching come back on | They are built, tested and switched off. They need a back end, moderation and a payment rail before they are honest. | Ship this release first. It earns the store accounts, the closed test and real users, and none of that work is repeated later.

## Known gaps
The honest list, as of 24 September 2026
What is not finished | Blocks launch? | What it means for you
No crash reporting | No, but risky | The release guide calls a crash during review the single largest rejection bucket, and you cannot see crashes your testers hit. Worth adding before the closed test. Ask me and it is an afternoon.
No dish carries allergen data | No | The safety guard is correct and the content behind it is missing, so the moment a woman saves an allergy, Eat can suggest nothing and log nothing. The screens say so out loud. Authoring the allergens is a content job, not a code job.
The severe cycle day cites British NHS guidance | No | Wrong country. It needs an Egyptian care source, or a clinician willing to sign off the citation.
A few controls say "not connected in this build" | No | Sharing a recipe or the grocery list, and the recipe steps. They are honest notices rather than dead buttons, but a reviewer may still call them out.
Speech input on the food logger cannot hear | No | The microphone offers the keyboard instead. It is honest, and it is one package away when you want it.
Notifications cannot notify | No | The screen is real, the plugin is not there. Nothing in this release needs to notify her.
The font licences are registered but not shown | No | Two open licence fonts are registered in code, and nothing displays them. A licences page is small and I can add it.
No Firebase, so nothing is on a server | No, by design | Everything lives on her phone. It is why this release can go out without a backend, and it is also why the community and coaching are switched off.

## Later, release 2
Parked: the back end, and everything that depends on it
This is the path the 22 September sheet described. None of it is wasted, and none of it is needed to put the first release on both stores.
What it unlocks: accounts and sign up, the national ID verification, the community, the coach side, the marketplace, coaching payments, and the assistant. All of it is already built, tested and switched off behind one flag set each.
The order, when you want it:
1. Install Java and the Firebase tools, and create the Firebase project.
2. Create Firestore. The region is permanent: me-central1 or me-central2 if offered, otherwise europe-west.
3. Turn on Storage, and phone number sign in restricted to Egypt only.
4. Set a budget alert before switching on anything billable.
5. Register the Android and iPhone apps, and hand me the two config files.
6. Deploy the security rules and indexes that are already written in firebase/.
7. I move the app from its local snapshot onto Firestore, keeping the snapshot as the offline cache.
8. Contract an identity provider for the ID check, and a payment provider for coaching.
9. Turn the flags back on, one release at a time, community before coaching.
The Gemini key for the assistant and the Paymob account for coaching belong at the very end, and the key never goes into the app: it is read by a Cloud Function.