## Start here
Own Hub, what is left and who does it
Replaces OWN-HUB-LAUNCH-CHECKLIST.xlsx, which was written for a release with no accounts.
What changed
The cut-down first release is cancelled. Own Hub now signs women in with a phone number and checks the Egyptian national ID and a live face before anyone gets in. That is built. It is not yet proven.
Where it stands today
The Firebase project own-hub is live, with the database in Frankfurt and the security rules deployed. Phone sign-in is real. Her training, meals and cycle sync to her own documents. The identity check runs entirely on our own servers rather than a paid provider: about 0.0031 US dollars a woman, roughly 157 dollars for the first fifty thousand, against a ceiling of 2,500.
3,903 app tests, 193 security-rules tests and 278 back-end tests pass. The analyser is clean. None of that means a real woman has been through the flow with a real card, because nobody has.
The one number that matters most
Nothing has been measured on an Egyptian ID card photographed on an Egyptian phone. Until the pilot runs there is no honest false-accept or false-reject rate for this product, and every threshold in it is a reasoned guess rather than a measurement.
How to read the tabs
"Your actions" is everything waiting on you, cheapest and most blocking first. "Decided" records the calls already made, so nobody reopens them by accident. "Not ready" is the honest list of what is unproven. "Mine" is what I still owe you.
One sequencing rule, and it is the expensive one to get wrong
The switch that closes the app to unverified women is built and deliberately OFF. Turn it on only after the functions are deployed and one real account has been verified end to end. Flip it early and every woman lands on a waiting screen for a call nothing books, and the app looks completely normal from the outside.

## Your actions
Everything waiting on you
Ordered by what unblocks the most for the least money. Green costs nothing. Orange costs money. Purple is a decision, not a task. Red blocks a release outright.
# | What | Exactly what to do, and why it matters | Done when | Cost | Status
1 | Android signing key: DONE | Created 25 September at ~/keys/ownhub-upload.jks. Verified: a real release bundle now builds and is signed with THIS key, not the debug fallback. The certificate in the built .aab reports SHA-1 4B:57:94:AC:43:69:76:65:3B:E7:89:B6:D3:81:69:F0:6C:D4:6F:7A, which matches your keystore exactly. Two things to keep doing: the password and the .jks belong in a password manager AND somewhere offline, because losing both with Play App Signing off means the app can never be updated again. And android/key.properties lives outside git on purpose, so when this work moves out of the temporary worktree you will need to place that file again. Cosmetic note, not worth redoing the key for: the certificate carries country code "ci" rather than "EG". Nothing reads it, Play does not check it, and it is never shown to anyone. | Done | Free | DONE
2 | Signing fingerprints: DONE for the upload key | All four are registered against the Android app: the debug pair so development works, and now your release pair so phone sign-in survives a release build. STILL OUTSTANDING, and it will not bite until you open the Play Console: Google generates its OWN certificate for Play App Signing, and that one must be registered too. Play Console, Setup, App signing. Registering only the upload key is the classic failure where everything works from your machine and sign-in breaks for everyone who installs from the Play Store, which is not an obvious symptom to trace back to a certificate. | Upload key done; Play App Signing cert still to come | Free | PART DONE
3 | Turn on App Check | THIS IS NOW THE ONE THING BLOCKING A REAL TEST. The seven functions are deployed and live in europe-west3, and they refuse every call that arrives without an App Check token, on purpose. Until a provider is registered, the app cannot talk to its own back end and nobody can be verified, including you. There are two layers and they need different things: TO TEST NOW, free: a debug token. Firebase console, App Check, then register a debug token for the simulator or your handset. Works without either store account, and is refused in a release build by design. Tell me when it is there and I will walk one account end to end. FOR PRODUCTION: Play Integrity on Android, which needs the Play Console account in step 10, and App Attest on iOS, which needs the Apple account in step 9. So the real providers are gated behind the two paid accounts, and the debug token is how you see the flow work before paying anybody. | A debug token is registered and I can reach the functions | Free | BLOCKS TESTING
4 | Budget alert: DONE | Set by the owner on 25 September. Worth knowing what normal looks like so an alert means something: the measured cost is about 0.0031 US dollars per woman verified, so roughly 157 dollars for the first fifty thousand. Anything more than a few dollars in the early days means something is looping, not that the app is popular. | Done | Free | DONE
5 | Rotate the Cloudflare API token | The token you pasted into the chat is compromised and must be treated as public. Delete it in the Cloudflare dashboard and create a new one. Do not send me the new one: if I need Cloudflare, you run the command. | The old token is deleted | Free | Not started
6 | Publish the four legal pages | The site is built and waiting in site/: home, privacy, terms, support and delete-account, in English and Arabic, with real right-to-left Arabic and zero external requests. Cloudflare Pages has a free tier with no card. Publish, then I fill lib/config/legal_links.dart and the app stops failing its own preflight. A missing or broken support page is one of the three most common reasons a first submission is rejected. | All four open on a phone, not just on your Mac | Free | Not started
7 | Have an Egyptian lawyer read the policy and terms | This outranks everything else on this sheet. All three source documents open with a line saying they have not been read by an Egyptian lawyer and must be before publication. I did not publish that banner, because a live policy announcing it is unreviewed is worse than none, but the instruction stands. Ask specifically: does a discard-immediately architecture with a foreign processor reduce our exposure under PDPL articles 12 and 14, and should we file the moment the licensing portal opens? | Counsel has signed off the privacy policy and terms | Lawyer fee | Not started
8 | Three legal values the site needs | The site has three visible gaps only counsel can fill: the court or governorate for disputes, the liability cap (the app is free, so the usual "what you paid us" cap is zero and counsel must decide whether that stands in Egypt), and the Data Protection Centre's current complaint channel. One edit to site/config.json each. | All three filled and the site rebuilt | Lawyer fee | Blocked by 7
9 | Apple Developer Program | 99 US dollars a year. Needed for the App Store, for TestFlight, and for the APNs key that removes the reCAPTCHA web page from the middle of sign-up. Apple verifies the account holder's identity, and that holder is you, not Rahma: Google and Apple both publish the account holder's legal name. Approval takes one to two days, so start it before you need it. | You can sign in to App Store Connect | 99 USD / yr | Not started
10 | Google Play Console | 25 US dollars once. Identity verification takes one to three days, and then Google requires a 14-day closed test with 12 real testers before you may go to production. That 14 days is a queue you cannot shorten, so open this account earlier than feels necessary. | You can create the app listing | 25 USD once | Not started
11 | Find the women who will do the reviews | Not a technical step, and the one most likely to be discovered too late. Anything the automatic check cannot settle becomes a short video call with a woman reviewer. At fifty thousand sign-ups, every one percent of flag rate is 500 calls. The reviewers must be women, and they need a script and a rota before the first one arrives. | You know who does the calls and when | Their time | Not started
12 | AWS account | NOT NEEDED. Listed because you asked. The original plan used Amazon for liveness at about 0.015 dollars a check; you chose the self-hosted challenge instead, so there is no Amazon in this product at all. Amazon has also been removed from the consent screen, because naming a processor you do not use is consent you would have to withdraw and take again. | Nothing to do | None | Not needed
13 | Say yes or no to the app icon | There is one: a typographic monogram in the brand rose, drawn from the product's own design language, because the project has never had a logo file. If you have a mark, hand me a 1024 by 1024 PNG with no transparency and every size regenerates in a minute. If not, the one there ships. | You have said keep or replace | Free | Not started
14 | Back end, already live | Nothing to do. Recorded so the sheet matches reality: the seven identity functions are deployed to europe-west3 and ACTIVE, the ID pepper is in Secret Manager as a 48 byte random value that has never been printed anywhere, Cloud Vision is enabled, and the security rules are live including the fix for a hole that let any signed-in account read any woman's training plans. An unauthenticated call to start_verification is refused by the function's own auth check, which is what it should do. | Nothing to do | Done | Done

## Decided
Decisions already made
Recorded so nobody reopens them by accident, including me.
Question | Your answer | What follows from it
How liveness works | Our own challenge. No AWS, at any price. | Costs nothing per check and needs no second cloud provider or dollar card. Weaker than a commercial model against a video replay or a mask, so uncertain cases go to a woman reviewer instead.
Where the gate sits | The whole app. She cannot use it before verifying. | Strongest safety claim, and it carries a real App Store risk: guideline 5.1.1(v) forbids requiring personal information to use an app unless it is core functionality. The argument that a women-only product qualifies is decided by one reviewer. Recorded as an accepted risk.
Storing photographs for review | Never. Not even for flagged cases. | The evidence bucket was deleted outright rather than left switched off, because a dormant path that writes ID photographs is what gets turned on by accident later. A reviewer therefore sees no picture: review is a live video call, which is what the niqab route already offered.
Which identity provider | None. Self-hosted. | The cheapest vendor quote was about 15,500 dollars at fifty thousand women. Ours measures at 157. Cloud Vision reads the card, the sex digit is arithmetic, and the face match is a model inside our own function.
Where the pilot runs | The production project, data deleted afterwards. | Test identities, test claims and test cost-ledger rows will exist in own-hub. Accepted knowingly. Worth deleting before the first real woman signs up, not after.
The content catalogue | You fill it later. | One programme exists where the code says twelve to twenty are needed, and no dish carries allergen data, so the allergy question currently empties the Eat tab. The admin console is built and waiting. This is authoring work, not engineering, and it is the real critical path to a release.
Sign-in method | Phone number and a six-digit code. | Sixteen screens were already built around it. The SMS is billed per message and sits OUTSIDE the 0.05 cap, because it is spent before the check begins. The exact Egyptian rate is still unknown: read it off your first real bill rather than trusting an estimate, mine included.

## Not ready
What is not proven yet
Everything here is built. None of it has met a real woman with a real card. This is the gap between "the tests pass" and "it works".
Gap | What it means
The pilot has never run | No false-accept or false-reject rate exists for this product on this population. The spec asks for 50 genuine women, 20 men with their own cards, 20 impostor attempts and 20 spoof attempts. Until that runs, every threshold is a reasoned guess.
The adversarial cases are unexecuted | Eleven of them, in MANUAL_QA.md: a man with his own card, a man with a consenting woman's card, a printed photo, a video replayed on a screen, a photocopy, a modified client, two accounts on one card, glasses, hijab, niqab. Each needs a pass or fail before launch.
A forged card defeats the design | If someone makes a convincing fake card carrying a man's photograph and an even 13th digit, nothing in this system catches it. There is no hologram or UV check, and Egypt offers no public validation API to private companies. Stated plainly because it will not be fixed by more engineering.
The functions are not deployed | They pass 278 tests locally and have never run in the cloud. Until they deploy, the app cannot verify anyone, which is exactly why the gate is still switched off.
Nobody has walked the flow on a real phone | Framing thresholds for the card, the dwell time on each challenge step, and the front-camera rotation for face detection are all unmeasured. If the rotation sign is wrong, the selfie step finds no face at all while the card works perfectly.
The photograph touches disk for milliseconds | The camera plugin has no in-memory shutter, so the file exists briefly before being deleted. The honest claim is "deleted immediately", not "never written". Worth knowing before anyone writes marketing copy.
The licence Egyptian law requires cannot be applied for | PDPL article 12 requires a licence from the Data Protection Centre to process biometric data. The portal was announced for June 2026 and has never opened. Every Egyptian company is in the same position. The defensible posture is minimisation plus a lawyer's memo on file, which is why step 7 matters.
Release preflight: 30 pass, 2 fail | Both remaining failures are yours and neither is code. "Team id filled in" needs the Apple Developer account (step 9). "Legal links filled in" needs the four pages published (step 6), after which I fill one file. Everything else passes, including the checks that matter most on Android: every 64-bit library is 16 KB aligned, R8 minification is on, and the bundle is signed with your upload key.

## Mine
What I still owe you
No action needed from you on these.
Item | State
Deploy the verification functions | Ready to deploy. Needs a Secret Manager secret for the ID pepper first, which I create, and the App Check providers from your step 3.
Choose the thresholds | In progress. Chosen from published benchmarks and reasoning, and marked in the code as provisional until the pilot measures them.
Cut the review volume | In progress. Several things that currently flag for review are not suspicious at all, they are just failed OCR: an unreadable sex word should ask for a clearer photograph, not a video call. Separating those two is what keeps the review queue survivable.
Verify one account end to end | After deployment. This is the gate that must pass before the whole-app switch is flipped.
Fill lib/config/legal_links.dart | One edit, as soon as your four pages are live.
The store disclosure drafts | Deliberately not written yet. Apple privacy labels and the Play Data safety form both need the final processor list and the SMS cost, and a privacy disclosure drafted from guesses is worse than none.